Automation Test Estimation Framework

| Prepared by/Modified by | Role | Date of preparation/ Modification |
| --- | --- | --- |
|  | Test Manager | dd/mmm/yyyy |
| Reviewed by | Role | Date of Review |
| Reviewer 1 Reviewer 2 | Project Manager Test Lead | dd/mmm/yyyy |
| Approved by | Role | Date of Approval |
|  | Head | dd/mmm/yyyy |
| Circulation List | Group1, Group2 |
| Version number of the work product | 1.0 |

TABLE OF CONTENTS

1.	Introduction	3

2.	Objective	3

3.	ProjectName Test Activities	4

4.	Size Estimation	6

5.	Productivity	8

6.	Effort Estimation	10

7.	Conclusion	14

8.	Assumptions	14

9.	Appendix	14

10.	Revision History	15

# Introduction

Testing is the mechanism by which defects can be found during execution of the application, which are undetected during reviews in different stages of software development.

This document is an attempt to come out with test estimation framework that has a sound basis and which is more aligned to ProjectName testing requirements.

The proposed estimation framework is based on the current set of testing activities carried out as part of ProjectName testing. If the activities change [scope, no. Of activities, type of activities etc] in future, the estimation framework has to be modified as appropriate.

# Objective

This document introduces an estimation framework for ProjectName testing activities. The goal of this estimation framework is to:

- Identify the major testing activities that are carried out as a part of ProjectName testing.

- Arrive at Size estimation for each work product pertaining to all the testing activities.

- Based on empirical data, compute productivity for each work product pertaining to all the testing activities.

- Arrive at Effort estimation for each work product pertaining to all the testing activities.

# ProjectName Test Activities

The following table provides the list of testing activities that are carried out in ProjectName during the various ProjectName-PLM stages. The “White Box” activities are newly identified for future needs.

| ProjectName PLM Stage | Test Activities | Comments |
| --- | --- | --- |
| M0 | None | ProjectName Test team is not involved in this phase. |
| M1 | Understanding SRD/PRD and FS | Identify test requirement by going through SRD/PRD, FS documents and participating in relevant Fagan reviews / JAD sessions. |
| M1 | Prepare Master Test plan | Contains test requirements [Functional / Performance / Security / Compatibility] for the product, test strategy, test environment, overall test schedule and plan. |
| M1 | Review Master Test Plan | Review for completeness based on test requirements |
| M2 | Black Box Testing: Prepare functional test plan | Functional test plan is prepared for critical features of the product. |
| M2 | Review functional test plan | Review for completeness based on functional test requirements |
| M2 | Black Box Testing: Prepare Functional Test Case documents | It contains test cases pertaining to all test requirements (PRD/SRD) It also traces the test cases to product requirements (PRD/SRD) |
| M2 | White Box Testing: Design of test cases | Create unit test design document (The JUNIT test framework can be used for testing Java code) |
| M2 | Prepare QTP Scripts: Black Box Test cases. | Identify features, which can be automated using QTP. Define Actions and data sets for the identified features Identify Workflows Create/Update Global Object File Create QTP Scripts (VBScript)VB (according to data driven test technique) Add checkpoints and update shared object repository Integrate in the QTP framework |
| M2 | Review and Update Functional Test Case documents. | Read the updated requirements document or PCR Update the traceability matrix Identify and remove Obsolete test cases Identify Updates to existing test cases Identify new test cases |
| M2/M3 | Prepare Test Data | Read the test case doc(Functional, Performance, Security, Compatibility) Identify the data requirement for each kind of testing |
| M3 | White Box Testing: implementation of test code | Coding of white box test cases using JUnit framework. Creation of test data sets for white box testing |
| M3 | Setting up Test Environment | Setup Performance test environment Setup Functional test environment Setup Unit test environment Setup Integration test environment |
| M3 | Execute manual Functional Test Cases for Desktop. | Set the test environment Configure user Execute the tests |
| M3 | Execute QTP scripts (Functional Test Cases) for Desktop. | Set the test Framework Execute the tests |
| M3 | Execute manual Functional Test Cases for Devices. | Configure Devices Execute the tests |
| M3 | Execute QTP scripts (Functional Test Cases) for Devices. | Using device simulators / browsers on desktop. |
| M3 | Performance testing using Spider tool. | Identify no. of users to be simulated Create Spider Sessions (50 user/ session is limit) Execute the tests |
| M3 | Perform V&V (Verification & Validation) | Go through V&V bugs that are fixed Identify V&V tests Setup Test Environment Execute V&V tests |
| M3 | Perform incremental & regression testing | Go through regression bugs that are fixed Identify regression tests Setup Test Environment Execute regression tests |
| M3 | Log and Report Test execution results. | Bugs are filed in the defect tracking system - Bugzilla. Provide test summary reports in the form of an excel sheet. |
| M3 | Defect Triage involvement | Participation in defect prioritization. |
| M4/M5 | None | ProjectName Test team is not involved in this phase. |

# Size Estimation

In this section we have come out with the definition of “Size” for each of the test activities identified in the previous section.

| ProjectName PLM Stage | Test Activities | Activities for arriving at Sizing / Work Product Items | Work product size |
| --- | --- | --- | --- |
| M0 | None (ProjectName Test team is not involved in this phase.) | None (ProjectName Test team is not involved in this phase.) | N/A |
| M1 | Understanding SRD/PRD and FS | N/A | N/A |
| M1 | Prepare Master Test plan | Master Test Plan document will contain high level 1) Test requirements [Functional / Performance / Security / Compatibility], 2) Test Strategy, 3) Test Environment, 4) QA Review Plan, 5) Resourcing & 6) Scheduling. | Sizing not applicable ( To obtain data based on past history ) |
| M1 | Review Master Test Plan | Review Record | Sizing not applicable ( To obtain data based on past history ) |
| M2 | Black Box Testing: Prepare functional test plan |  | Sizing not applicable ( To obtain data based on past history ) |
| M2 | Review functional test plan |  | Sizing not applicable ( To obtain data based on past history ) |
| M2 | Black Box Testing: Prepare Functional Test Cases. (for a given feature.) | (1) Identify test items (Usually one test item per use case) for a given use case. (2) Identify test scenarios for each of the test item. (Typically there are at least three scenario’s for a given test item viz. Functional test scenario, Alternate test scenario, Exceptional test scenario. For example in some cases, there will be multiple sets of the above three test scenario categories.) (3) Identify and compute number of test cases under each scenario depending on the corresponding test requirements. | Total # of test cases / tests |
| M2 | White Box Testing: Design of test cases | 1) Identify the packages, classes or functions which need white box testing 2) Identify Asserts in the same. 3)Design a fixture or test suite for the same 4)Create unit test design document | Total # of Asserts per class Total # of i/o for total no. of test cases(Asserts) Per class |
| M2 | Prepare QTP Scripts: Black Box Test cases. | Identify Workflow Identify number of unique actions (one action equivalent to test case) Associate actions with workflow. Arrive at SLOC based on actions. | QTP Source Lines Of Code. |
| M2 | Review and Update Functional Test Case documents. | Review regression suite Update regression suite Review functional test case Update functional test case | Total # of regression test cases Total # of functional test cases |
| M2/M3 | Prepare Test Data [user data creation, content data creation etc.] | Pst files, nsf files, attachments of various application types, QTP scripts for user data generation | Sizing not applicable |
| M3 | White Box Testing: implementation of test code | Coding of white box test cases using JUnit framework. Creation of test data sets for white box testing (The JUNIT test framework can be used for testing Java code) | Java Source lines of code OR # of JUnit Classes |
| M3 | Setting up Test Environment | Setup Performance test environment Setup Functional test environment Setup Unit test environment Setup Integration test environment | Sizing not applicable |
| M3 | Execute Functional Test Cases | Desktop Test Execution | Total # of executed test cases |
| M3 | Execute Functional Test Cases | Execute QTP scripts (Functional Test Cases) for Desktop. | Total # of executed test cases |
| M3 | Execute Functional Test Cases | Device Test Execution | Total # of executed test cases |
| M3 | Execute Functional Test Cases | Execute QTP scripts (Functional Test Cases) for Devices. | Total # of executed test cases |
| M3 | Performance testing | 1) Identify product areas whose throughput will be tested 2) Identify product areas which will stress tested 3) Identify product areas which will Load tested | Delphi technique will be used |
| M3 | Perform V&V (Verification & Validation) | V&V test report | Total # of executed V&V test cases |
| M3 | Perform incremental & regression testing | Regression test report | Total # of executed regression test cases |
| M3 | Log and Report Test execution results. | Updated bugzilla defect entries & consolidate test reports | Total # of defects updated / added in bugzilla |
| M3 | Defect Triage involvement | Participation in defect prioritization. | Sizing not applicable |
| M4/M5 | None (ProjectName Test team is not involved in this phase.) | N/A (ProjectName Test team is not involved in this phase.) | N/A |

# Productivity

This section outlines the productivity for the test activities, which are carried out at ProjectName. The data was computed based on empirical data based on Razor & Unifi releases in the past. The productivity (figures are based on average productivity viz. Averaged out across complexities of requirements.

| ProjectName PLM Stage | Test Activities | Work Product Items | Average Productivity |
| --- | --- | --- | --- |
| M0 | None (ProjectName Test team is not involved in this phase.) | N/A | N/A |
| M1 | Understanding SRD/PRD and FS | N/A | N/A |
| M1 | Prepare Master Test plan | Master Test Plan document | N/A |
| M1 | Review Master Test Plan | Review Record | N/A |
| M2 | Black Box Testing: Prepare functional test plan | Functional Test Plan document | N/A |
| M2 | Review functional test plan | Review Record | N/A |
| M2 | Black Box Testing: Prepare Functional Test Cases. (For a given feature.) | 1) Identify test items (Usually one test item per use case) for a given use case. (2) Identify test scenarios for each of the test item. (Typically there are at least three scenario’s for a given test item viz. Functional test scenario, Alternate test scenario, Exceptional test scenario. For example in some cases, there will be multiple sets of the above three test scenario categories.) (3) Identify number of test cases under each scenario depending on the corresponding test requirements. | 3 to 4 test cases per hr (For writing test cases ) |
| M2 | White Box Testing: Design of test cases | 1) Document which will no. of packages, classes and function to be tested with Assert candidate And I/O details | 3 to 4 Classes per hour |
| M2 | Prepare QTP Scripts. (Black Box Test cases.) | (1) Identify Workflow (2) Identify number of unique actions (one action equivalent to test case) (3) Associate actions with workflow. (4) Arrive at SLOC based on actions. | 10 QTP Source Lines of Code per hour. |
| M2 | Review and Update Functional Test Case documents. | Update functional test case | 3 to 4 test case per hour |
| M2/M3 | Prepare Test Data [user data creation, content data creation etc.] | Pst files, nsf files, attachments of various application types, QTP scripts for user data generation | 20 email or PIM data / hour 20 Admin setting / hour |
| M3 | White Box Testing: implementation of test code | 1) JUnit source code | 60 Lines of JUnit Code/Day with (all asserts and comments) |
| M3 | Setting up Test Environment | Setup Performance test environment Setup Functional test environment Setup Unit test environment Setup Integration test environment | N/A |
| M3 | Execute Functional Test Cases - Manual Testing on Desktop | Desktop Test Execution (Manual Testing) | 5 to 6 test cases execution per hour. |
| M3 | Execute Functional Test Cases - Automated Testing on Desktop | Desktop Test Execution (Automated Testing) | 40 to 50 test cases execution per hour. |
| M3 | Execute Functional Test Cases – Manual Testing on Devices | Device Test Execution (Manual Testing) | 3 to 4 test cases execution per hour |
| M3 | Execute Functional Test Cases – Automated Testing on Devices | Device Test Execution (Automated Testing) | Note: QTP scripting on device emulators is work in progress. Right now productivity data not available. |
| M3 | Performance testing | Test Reports for transaction latencies Test reports for maximum load Test report for optimal Configuration | 5 to 6 test cases execution per hour |
| M3 | Perform V&V (Verification & Validation (Manual Desktop Testing) | V&V test report | 5 to 6 test cases execution per hour. |
| M3 | Perform V&V (Verification & Validation (Manual Device Testing) | V&V test report | 3 to 4 test cases execution per hour |
| M3 | Perform incremental & regression testing Desktop, Manual testing. | Test Summary report | 5 to 6 test cases execution per hour. |
| M3 | Perform incremental & regression testing Desktop, Automated testing. | Test Summary report | 40 to 50 test cases execution per hour. |
| M3 | Perform incremental & regression testing Device, Manual testing. | Test Summary report | 3 to 4 test cases execution per hour |
| M3 | Perform incremental & regression testing Device, Automated testing. | Test Summary report | Note: QTP scripting on device emulators is work in progress. Right now productivity data not available. |
| M3 | Log and Report Test execution results. | Updated bugzilla defect entries & consolidate test reports | 4-5 defects / hr [bugzilla entries / updates] |
| M3 | Defect Triage involvement | Participation in defect prioritization. | Productivity not applicable |
| M4/M5 | None (ProjectName Test team is not involved in this phase.) | N/A (ProjectName Test team is not involved in this phase.) | N/A (ProjectName Test team is not involved in this phase.) |

# Effort Estimation

Once the size of each work product is estimated (as outlined in previous section), the next step is to arrive at the effort in person hours. There are two scenarios here: One scenario where we have the empirical data for the Productivity for the activities and the other where we do not have any empirical data. In the second scenario, we have to rely on “Wide Band Delphi Technique” for estimation. This technique for arriving at effort estimation is based on effort estimates arrived independently by three engineers and consolidating them in a effort estimate meeting chaired by a moderator.

| ProjectName PLM Stage | Test Activities | Work Product Items | Size Units [A] | Productivity [B] | Effort in Person Hours. |
| --- | --- | --- | --- | --- | --- |
| M0 | None (ProjectName Test team is not involved in this phase.) | N/A | N/A | N/A | N/A |
| M1 | Understanding SRD/PRD and FS | Total # of test requirements [Functional + Performance + Security + Compatibility] | N/A | N/A | This will be computed at the start of M1. The estimates depend on size of the SRD/PRD/FS items. The effort estimates are based on “Wide Band Delphi Technique” ( Effort estimates computed separately by three engineers ) |
| M1 | Prepare Master Test Plan | Test requirements, Test Strategy, Test Environment, QA Review Plan, Resourcing & Scheduling. | N/A | N/A | This will be computed at the start of M1. The estimates depend on size of the SRD/PRD/FS items. The effort estimates are based on “Wide Band Delphi Technique” ( Effort estimates computed separately by three engineers ) |
| M1 | Review Master Test Plan | Review Record | N/A | N/A | The effort estimates are based on “Wide Band Delphi Technique” ( Effort estimates computed separately by three engineers ) |
| M2 | Black Box Testing: Prepare functional test plan | Functional Test Plan document | N/A | N/A | The effort estimates are based on “Wide Band Delphi Technique” ( Effort estimates computed separately by three engineers ) |
| M2 | Review functional test plan | Review Record | N/A | N/A | The effort estimates are based on “Wide Band Delphi Technique” (Effort estimates computed separately by three engineers) |
| M2 | Black Box Testing: Prepare Functional Test Case documents. | (1) Identify test items (Usually one test item per use case) for a given use case. (2) Identify test scenarios for each of the test item. (Typically there are at least three scenario’s for a given test item viz. Functional test scenario, Alternate test scenario, Exceptional test scenario. For example in some cases, there will be multiple sets of the above three test scenario categories.) (3) Identify and compute number of test cases under each scenario depending on the corresponding test requirements. | Total number of test cases / tests | 3 to 4 test cases / tests per hour. | [A] Divided by [B] will provide the effort in person hours. |
| M2 | White Box Testing: Design of test cases | 1) Identify the packages, classes or functions which need white box testing 2) Identify Asserts in the same. 3) Design a fixture or test suite for the same 4) Identify whether specific input/output needs for testing if yes then verify if any other framework can be utilized (e.g. Cactus Framework) | Total # of Asserts per class (A1) Total # of i/o for total no. of test cases(Asserts) Per class (A2) Here A=A1+A2 | 3 to 4 Classes per hour | [A] Divided by [B] will provide the effort in person hours ( Here A=A1+A2 ) |
| M2 | Prepare QTP Scripts. (Black Box Test cases.) | (1) Identify Workflow (2) Identify number of unique actions (one action equivalent to test case) (3) Associate actions with workflow. (4) Arrive at SLOC based on actions. | Total QTP Source Lines of Code | 10 QTP Source Lines of Code per hour. (Based on past three months empirical data) | [A] Divided by [B] will provide the effort in person hours. |
| M2 | Review and Update Functional Test Case documents. | Update functional test case | Total number of test cases | 3 to 4 tests per hour | [A] Divided by [B] will provide the effort in person hours |
| M2/M3 | Prepare Test Data [user data creation, content data creation etc.] | Pst files, nsf files, attachments of various application types, QTP scripts for user data generation | N/A | N/A | This will be computed at the start of M3. The estimates depend on size of the SRD/PRD/FS items. The effort estimates are based on “Delphi Technique” (Effort estimates computed separately by three engineers) |
| M3 | White Box Testing: implementation of test code | 1) JUnit source code | # of JUnit Classes | 60 Lines of JUnit Code/Day with (all asserts and comments) | [A] Divided by [B] will provide the effort in person hours |
| M3 | Setting up Test Environment | Setup Performance test environment Setup Functional test environment Setup Unit test environment Setup Integration test environment | N/A | N/A | The estimates depend on size of the SRD/PRD/FS items. The effort estimates are based on “Delphi Technique” (Effort estimates computed separately by three engineers) |
| M3 | Execute Functional Test Cases - Manual Testing on Desktop | Desktop Test Execution (Manual Testing) | No of test cases executed per hour. | 5 to 6 test cases execution per hour. | [A] Divided by [B] will provide the effort in person hours. |
| M3 | Execute Functional Test Cases – Manual Testing on Devices | Device Test Execution (Manual Testing) | No of test cases executed per hour. | 3 to 4 test cases execution per hour | [A] Divided by [B] will provide the effort in person hours. |
| M3 | Execute Functional Test Cases - Automated Testing on Desktop | Desktop Test Execution (Automated Testing) | No of test cases executed per hour. | 40 - 50 test cases execution per hour. ( Based on past three months empirical data ) | [A] Divided by [B] will provide the effort in person hours. |
| M3 | Execute Functional Test Cases – Automated Testing on Devices | Device Test Execution (Automated Testing) | No of test cases executed per hour. | Note: QTP scripting on device emulators is work in progress. Right now productivity data not available. | Note: QTP scripting on device emulators is work in progress. Right now productivity data not available |
| M3 | Performance testing | Test Reports for transaction latencies | Delphi technique will be used | 5 to 6 test cases execution per hour | [A] Divided by [B] will provide the effort in person hours |
| M3 | Perform V&V (Verification & Validation (Manual Desktop Testing) | V&V test report | No of test cases executed per hour. | 5 to 6 test cases execution per hour. | [A] Divided by [B] will provide the effort in person hours. |
| M3 | Perform V&V (Verification & Validation (Manual Device Testing) | V&V test report | No of test cases executed per hour. | 3 to 4 test cases execution per hour | [A] Divided by [B] will provide the effort in person hours. |
| M3 | Perform incremental & regression testing Desktop, Manual testing.. | Test Summary report | No of test cases executed per hour. | 5 to 6 test cases execution per hour. | [A] Divided by [B] will provide the effort in person hours. |
| M3 | Perform incremental & regression testing Desktop, Automated testing. | Test Summary report | No of test cases executed per hour. | 40 to 50 test cases execution per hour. | [A] Divided by [B] will provide the effort in person hours. |
| M3 | Perform incremental & regression testing Device, Manual testing. (Only for Maintenance cycles) Device, Manual testing. | Test Summary report | No of test cases executed per hour. | 3 to 4 test cases execution per hour | [A] Divided by [B] will provide the effort in person hours. |
| M3 | Perform incremental & regression testing (Only for Maintenance cycles) Device, Automated testing. | Test Summary report | No of test cases executed per hour. | Note: QTP scripting on device emulators is work in progress. Right now productivity data not available | Note: QTP scripting on device emulators is work in progress. Right now productivity data not available |
| M3 | Log and Report Test execution results. | Updated bugzilla defect entries & consolidate test reports | Total # of defects updated / added in bugzilla | 4-5 defects / hr [bugzilla entries / updates] | [A] Divided by [B] will provide the effort in person hours. |
| M3 | Defect Triage involvement | Participation in defect prioritization. | N/A | N/A | Total Effort varies depending on the number of Bugs/CR’s/Enhancements. ( It also depends on the number of participants in this activity ) |
| M4/M5 | None (ProjectName Test team is not involved in this phase.) | None (ProjectName Test team is not involved in this phase.) | N/A | N/A | N/A |

# Conclusion

With the proposed Test Estimation framework for ProjectName-QA in place, the following improvements can be expected:

The testing team will be able to arrive at a close-to accurate estimate, which will allow it to predict and manage schedules effectively.

The proposed estimation framework is based on the current set of testing activities carried out as part of ProjectName testing. If the activities change [scope, number of activities, type of activities etc] in future, the estimation framework has to be suitably modified.

# Assumptions

The estimation framework is for pure “Engineering” activities. Project management efforts are NOT taken into account.

# Appendix

The ExcelSheet workbook titled “ProjectName-TestEstimationWorkBook” would be used to capture size, productivity, effort estimation for each ProjectName-QA activity. This workbook also captures the effort summary for all the QA activities for a given project in the second worksheet.

Glossary:

The following are a list of glossary of terms used. (As used in the Unifi Test Case Documents)

Test Cases / Tests: This is lowest possible testing unit, denotes one unique action (with input data variations) according to ProjectName usage.

Test Data: Data that is used for carrying out testing (Manual or Automated). For example, test data pertains to Email content, PIM content or Admin Settings for ProjectName One Business Server.

Workflow:  It is defined as a set of test items, which have corresponding QTP scripts. Each QTP script represents an automated test scenario.

# Revision History

| Section Changed | Change Description | Revision Date | Version Number | Reviewed by | Approved by |
| --- | --- | --- | --- | --- | --- |
| Initial | Initial Version | dd mmm yyyy | Draft 1.0 | Testmanager/ProjectManager | DeliveryManager |